## 1_Activities
Ecomarinas - project scope
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
|  | Gdańsk Sports Centre (PL) | Pomeranian Voivodeship (PL) | West Pomeranian Voivodeship (PL) | Tolkmicko Commune - Suchacz Marina (PL) | Klaipeda University (LT) | Partner (DK) | Partner (DE) | Partner (SE)
WP 1 Management and coordination | bar: 1 to 8
A 1.1. | Substantive, finacial and administrative management | bar: 1
A 1.2. | Internal and external communication | bar: 1 to 5
A 1.3. | Reporting | bar: 1 to 5
WP 2 Capacity building | bar: 1 to 8
A 2.1. | Benchmarking and desk research | bar: 1 to 5
A 2.2. | Study visits in marinas | bar: 1 to 5
A 2.3. | Update of existing marina management guidelines based on experience from study visits | bar: 2
A 2.4. | Seminars for marinas administrators | bar: 3
WP 3 Pilot investments | bar: 1 to 8
A 3.1. | Research on eco-solutions in marinas management | bar: 1; 5
A 3.2. | Preparation of the investment | bar: 1; 4
A 3.3. | Pilot investment implementation | bar: 1 to 2; 4
WP 4 Education and awareness rising activities | bar: 1 to 8
A 4.1. | Exchange of good practice - identification of educational tools, creation of educational materials (workshops) | bar: 1 to 5
A 4.2. | Educational (awareness rising) activities for sailors visiting marinas | bar: 1; 4
A 4.3. | Maritime and ecological education for youth | bar: 1 to 3; 5
WP 5 Promotion and dissemination** | bar: 1 to 8
A 5.1. | Opening and final conferences | bar: 1 to 2
A 5.2. | Dissemination events | bar: 1 to 5
A 5.3. | Creation of visual identity
A 5.4. | Promotion by media tools | bar: 1 to 5
* work package coordinator
** promotion and dissemination will be applied in each WP